## Milestones and Tasks
Auction Fair Project Timeline
Project Start Date: | 2018-09-26
Project End Date: | 2018-12-05
Milestone: | Start Date: | End Date: | Duration: | Task: | Assigned to: | Comments:
1 | 2018-09-26 | 2018-10-03 | 7 | MEVN Stack Tutorial and Skeleton | Everyone
2 | 2018-10-03 | 2018-10-17 | 14 | Basic web app page layout |  | We also had 'add routes for pages' and 'connect to database' but that was a part of the MEVN tutorial
3 | 2018-10-17 | 2018-10-31 | 14 | Integrate CRUD with manage data page
3 | 2018-10-17 | 2018-10-31 | 14 | Connect display page to database, populate display page with data
3 | 2018-10-17 | 2018-10-31 | 14 | Writing tests unit and integration test
4 | 2018-10-31 | 2018-11-07 | 7 | Authentication and security for admin login |  | Decorators, routing pages after authentication
| 2018-10-31 | 2018-11-07 | 7 | Importing/exporting data with GUI
| 2018-10-31 | 2018-11-07 | 7 | Admin web page edit and manage database pages polished
5 | 2018-11-07 | 2018-11-14 | 7 | Additional layouts for monitor display
| 2018-11-07 | 2018-11-14 | 7 | Deploy raspberry pi on server laptop
6 | 2018-11-14 | 2018-11-21 | 7 | Troubleshoot and Testing
Formulas:
Start Date: = [End Date:, row above]
Start Date: = [Start Date:, row above]
End Date: = [Start Date:]+[Duration:]
End Date: = [End Date:, row above]